## Summary
metric | value
Total cleanings | 4
Total waiting time (min) | 15
Batches that wait | 1
Which batches wait | B004
Longest wait (min) | 15
Busy time per resource (min) | CIP_1: 240, CIP_2: 180
Idle time per resource (min) | CIP_1: 255, CIP_2: 315
Busiest resource | CIP_1 (48.5%)
Tightest batch (least slack left) | B003 (60 min left)
Setup time per cleaning (min) | 15
Schedule span (min) | 495

## Waiting batches
batch_id | equipment | resource | ready | start | waiting_min | latest_start | slack_left_min | blocked_by | reason | other_resources
B004 | EQ03 | CIP_2 | 2026-10-05 14:00 | 2026-10-05 14:15 | 15 | 2026-10-05 16:30 | 135 | B002 | CIP_2 busy with B002 until 14:15 (cleaning ends 14:00 + 15 min setup) | none (only option)

## Resource workload
resource | cleanings | cleaning_min | batches_waiting | waiting_min | first_start | last_end | setup_min | busy_min | idle_min | busy_% | idle_% | order
CIP_1 | 2 | 210 | 0 | 0 | 2026-10-05 12:00 | 2026-10-05 20:00 | 30 | 240 | 255 | 48.5 | 51.5 | B001 -> B003
CIP_2 | 2 | 150 | 1 | 15 | 2026-10-05 13:00 | 2026-10-05 15:45 | 30 | 180 | 315 | 36.4 | 63.6 | B002 -> B004

## Resource timeline
resource | order | batch_id | equipment | start | end | free_again_at | idle_before_min | waiting_min
CIP_1 | 1 | B001 | EQ01 | 2026-10-05 12:00 | 2026-10-05 13:30 | 2026-10-05 13:45 | 0 | 0
CIP_1 | 2 | B003 | EQ01 | 2026-10-05 18:00 | 2026-10-05 20:00 | 2026-10-05 20:15 | 255 | 0
CIP_2 | 1 | B002 | EQ02 | 2026-10-05 13:00 | 2026-10-05 14:00 | 2026-10-05 14:15 | 60 | 0
CIP_2 | 2 | B004 | EQ03 | 2026-10-05 14:15 | 2026-10-05 15:45 | 2026-10-05 16:00 | 0 | 15

## Equipment
equipment | cleanings | cleaning_min | waiting_min | tightest_slack_left_min
EQ01 | 2 | 210 | 0 | 60
EQ02 | 1 | 60 | 0 | 240
EQ03 | 1 | 90 | 15 | 135

## All batches
batch_id | equipment | resource | status | ready | start | end | latest_start | cleaning_min | waiting_min | slack_min | slack_left_min | blocked_by | reason | other_resources
B001 | EQ01 | CIP_1 | on time | 2026-10-05 12:00 | 2026-10-05 12:00 | 2026-10-05 13:30 | 2026-10-05 13:30 | 90 | 0 | 90 | 90 |  |  | none (only option)
B003 | EQ01 | CIP_1 | on time | 2026-10-05 18:00 | 2026-10-05 18:00 | 2026-10-05 20:00 | 2026-10-05 19:00 | 120 | 0 | 60 | 60 |  |  | none (only option)
B002 | EQ02 | CIP_2 | on time | 2026-10-05 13:00 | 2026-10-05 13:00 | 2026-10-05 14:00 | 2026-10-05 17:00 | 60 | 0 | 240 | 240 |  |  | CIP_1
B004 | EQ03 | CIP_2 | WAITS | 2026-10-05 14:00 | 2026-10-05 14:15 | 2026-10-05 15:45 | 2026-10-05 16:30 | 90 | 15 | 150 | 135 | B002 | CIP_2 busy with B002 until 14:15 (cleaning ends 14:00 + 15 min setup) | none (only option)

## Definitions
term | about | meaning
Waiting | equipment | Minutes between equipment being ready (production ended) and its cleaning starting
Slack | batch | Size of the allowed start window: latest start - earliest start (from the input data)
Slack left | batch | Slack - waiting. Room still left after scheduling; small = fragile
Busy | cleaning resource | Cleaning time + setup time. The resource cannot take another job
Idle | cleaning resource | Schedule span - busy time. Spare capacity, but possibly at the wrong hours
Span | whole schedule | From the first equipment ready time to the last time a resource is free again
Blocked by | batch | The previous cleaning on the same resource that is still running or flushing